## Planning
Date | Project |  |  | On Board | [28 empty] | Burndown Chart
[8 empty] | Sprint 1 | [6 empty] | Sprint 2 | [6 empty] | Sprint 3
Nr | Release | Sprint | User Story | Task / Story | Subtask | Conditions of Satisfaction | Estimated Points | 2014-11-17 | 2014-11-18 | 2014-11-19 | 2014-11-20 | 2014-11-21 | 2014-11-22 | 2014-11-23 | 2014-11-24 | 2014-11-25 | 2014-11-26 | 2014-11-27 | 2014-11-28 | 2014-11-29 | 2014-11-30 | 2014-12-01 | 2014-12-02 | 2014-12-03 | 2014-12-04 | 2014-12-05 | 2014-12-06 | 2014-12-07 | State | Owner | Tester | Completed
| In the release you describe what you need to hand show at the end of the week | The sprint is everything that need to be done in order to make the release | A user story describes what should be done (After this phase the customer has an overview of what the concept is going to be) | Task describe the main chuncks of work that need to be done | Break down tasks into subtask (Sketches --> board / cards / pawns / etc) | Here you describe what criteria need to be met, in order for the task to be completed to satisfaction (Our board gameboard design must be full color CMYK and A2 format | Points are estimates that show the priority of the task | [21 empty] | In a daily standup you check which tasks have been completed | The person responsible | The person responsible to see if conditions of satisfaction are met | Date of completion
| Avalilable Points | [5 empty] | 100
1 | Concept
1.1 |  | Game Design Document, Prototypes, functional and assets
1.1.1 |  |  |  | Game Design Document |  |  | 60
[5 empty] | Brainstorm | Come up with an idea with a game that is approved by everyone and stick with it | 30 | [21 empty] | Done | Team | Team | 2016-08-29
[5 empty] | Target Group Analysis | Decide on a suitable target group for the game | 4 | [21 empty] | Done | Team | Team | 2016-08-29
[5 empty] | Mechanics Analysis | Have suitable and logical mechanics | 8 | [21 empty] | Done | Team | Plamen | 2016-08-29
[5 empty] | Game Rules | Have a list of all the rules | 15 | [21 empty] | Done | Team | Slavi | 2016-08-31
[5 empty] | Game Concept Document | When it has fulfilled all applicable points. | 18 | [21 empty] | Done | Slavi | Team | 2016-09-05
1.1.2 |  |  |  | Moodboard |  |  | 8
[5 empty] | Moodboard Concept | Make a board with pictures discribing the art style | 2 | [21 empty] | Done | Tim | Mathilde | 2016-09-01
[5 empty] | Moodboard Discussion | Everyone agrees on the moodboard | 2 | [21 empty] | Done | Team | Team | 2016-09-01
1.1.3 |  |  |  | Sketches |  |  | 16
[5 empty] | Concept Art | We must have concept art for the map, characters, poster and cards. | 8 | [21 empty] | Done | Mathilde | Tim | 2016-09-05
[5 empty] | Character Design | We should have 3d models by Monday. | 8 | [21 empty] | Done | Tim | Jacqueline | 2016-09-05
[5 empty] | Cards/Tokens Design | Have final design of the tokens and cards. | 8 | [21 empty] | Done | Mathilde | Jacqueline | 2016-09-01
1.1.4 |  |  |  | Paper Prototypes |  |  | 48
[5 empty] | Playable version(s) | Have an A2 sized map, balanced rules for the game, character pieces and dices | 16 | [21 empty] | Done | Team | Team | 2016-09-02
1.1.9 |  |  |  | Scrum Meeting |  | Presented the game and next week's plan. | 10 | [6 empty] | 10 | [14 empty] | Done | Team | Team | 2016-09-02
2 | Design
Paper prototype
|  |  |  | Game Rules |  | Be done with the printed version by Tuesday. | [22 empty] | Done | Plamen | Slavi
|  |  |  | Concept art |  | When the 3D models and map are finalised. | [22 empty] | Done | Mathilde | Jacqueline | 2016-09-02
|  |  |  | Game test | [25 empty] | Team | Team
[5 empty] | Test sheet | Played a game. Added planned features with each. | [22 empty] | Done | Team | Team | 2016-08-31
[6 empty] | Played a game. Added planned features with each. | [22 empty] | Done | Team | Team | 2016-09-01
[6 empty] | Played a game. Added planned features with each. | [22 empty] | Done | Team | Team | 2016-09-02
[6 empty] | Played a game. Added planned features with each. | [22 empty] | Done | Team | Team | 2016-09-05
Paper Prototype
[5 empty] | Feedback forms | We haven't found anyone to test our game. | [22 empty] | Done | Team | Team | 2016-09-05
[5 empty] | Updated (final) version | It should be printed and corrections made on it. | [22 empty] | Done | Team | Team | 2016-09-05
Poster
[5 empty] | Design | When it's digital format | [22 empty] | Done | Jacqueline | Mathilda | 2016-09-07
[5 empty] | Print | When we have it physically. | [22 empty] | Done | Plamen | Slavi | 2016-09-07
|  |  |  | Trailer Design / Script | [24 empty] | Done | Slavi | Team | 2016-09-06
|  |  |  | Scrum Meeting |  |  | 10 | [13 empty] | 10 | [7 empty] | Done | Team | Team | 2016-09-07
3 | Production
Final design of the board
[5 empty] | Print | Print it on four A4 pages full color | 10 | [21 empty] | Done | Plamen | Slavi | 2016-09-07
[5 empty] | Assembly | We need the printed pages to be glued on the board | 10 | [21 empty] | Done | Plamen | Slavi | 2016-09-07
|  |  |  | Game Testing |  |  | 10
[5 empty] | Feedback forms | Get feedback about the game | [22 empty] | Done | Team | Team | 2016-09-06
|  |  |  | Poster |  |  | 10
[5 empty] | print | WHEN IT LOOKS GOOD AND IT'S PRINTED | [22 empty] | Done | Plamen | Slavi | 2016-09-07
|  |  |  | Pawns |  |  | 15
[6 empty] | 3D printed | [22 empty] | Done | Tim | Team | 2016-09-08
Trailer design
[5 empty] | Recording | Shoot the trailer in a nice and cozy place. | 10 | [21 empty] | Done | Plamen | Tim | 2016-09-08
[5 empty] | Montage | Zooms in and transitions into the game itself when an action happens like a player get in a trap. | 10 | [21 empty] | Done | Plamen | Team | 2016-09-08
|  |  |  | Rule Book |  | Printed on A5 pages full color with a hard cover | 15 | [21 empty] | Done | Plamen | Slavi | 2016-09-07
|  |  |  | Scrum Meeting |  |  | 10 | [20 empty] | 10 | Done | Team | Team | 2016-09-08
4 | Polishing, Final Build, and Delivery
Game manual
[5 empty] | Design | Does it look nice and well-made? | 10 | [21 empty] | Done | Plamen | Slavi | 2016-09-07
[5 empty] | Implement | wat | 10 | [21 empty] | Done | Plamen | Slavi | 2016-09-07
[5 empty] | Test | wat | 10 | [21 empty] | Done | Plamen | Slavi | 2016-09-07
|  |  |  | Game Testing and Tweaking |  |  | 20 | [22 empty] | Team | Team
[6 empty] | Are the rules balanced? | [22 empty] | Done | Team | Team | 2016-09-06
|  |  |  | Game Board |  |  | 20 | [22 empty] | Team | Team
[6 empty] | Is it foldable, colored and not trashed? | [22 empty] | Done | Team | Team | 2016-09-07
|  |  |  | Trailer |  |  | 10 | [22 empty] | Team | Team
[6 empty] | Is it interesting and does it represent the style of the game | [22 empty] | Done | Plamen | Team | 2016-09-08
|  |  |  | Presentation |  |  | 10 | [22 empty] | Plamen | Team
[6 empty] | Does it represent our game well? | [22 empty] | Done | Slavi | Team | 2016-09-08
|  |  |  | Scrum Meeting | Individual Contributions | Are we satisfied with how we have contributed? | 10 | [20 empty] | 10 | Done | Slavi | Team | 2016-09-09
[5 empty] | Individual Contributions | Are we satisfied with how we have contributed? | [22 empty] | Done | Plamen | Team | 2016-09-09
[5 empty] | Individual Contributions | Are we satisfied with how we have contributed? | [22 empty] | Done | Mathilda | Team | 2016-09-09
[5 empty] | Individual Contributions | Are we satisfied with how we have contributed? | [22 empty] | Done | Tim | Team | 2016-09-09
[5 empty] | Individual Contributions | Are we satisfied with how we have contributed? | [22 empty] | Done | Jacqueline | Team | 2016-09-09
This is new for us. :( We aren't scrum gods (yet).

## Burndown (hidden)
Project | On Board
Sprint 1
Date | Points
2014-11-16 | 100
2014-11-17 | 100 | 100
2014-11-18 | 100
2014-11-19 | 100
2014-11-20 | 100
2014-11-21 | 100
2014-11-22 | 100
2014-11-23 | 100
Sprint 2
Date | Points
2014-11-23 | 200
2014-11-24 | 200
2014-11-25 | 200
2014-11-26 | 200
2014-11-27 | 200
2014-11-28 | 200
2014-11-29 | 200
2014-11-30 | 200
Sprint 3
Date | Points
2014-11-30 | 100
2014-12-01 | 100
2014-12-02 | 100
2014-12-03 | 100
2014-12-04 | 100
2014-12-05 | 100
2014-12-06 | 100
2014-12-07 | 100
Sprint 4
Date | Points
2014-12-07 | 100
2014-12-08 | 100
2014-12-09 | 100
2014-12-10 | 100
2014-12-11 | 100
2014-12-12 | 100
2014-12-13 | 100
2014-12-14 | 100